## NASSTEC and PhD timeline
|  | 2015-05-01 | 2022-05-01 | 2029-05-01 | Jun-5 SF vacation family visit | 2012-06-01 | 2019-06-01 | Jun-26 3 days with BJA | 2003-07-01 | 2010-07-01 | 2017-07-01 | 2024-07-01 | 1931-07-01 | Aug-07 4 days with BJA | Aug-14 Final Thesis preparations to submit to Pavia by 20 Aug | 2021-08-01 | 2028-08-01 | 2004-09-01 | 2011-09-01 | 2018-09-01 | Final NASSTEC Conference Kew 01/09/2025
I. | Thesis |  |  | ✓skype with BJA and plan a strategy | [10 empty] | Final Thesis preparations to submit to Pavia by 20 Aug
| a. Introduction | send outline to co authors ✓ | ✓with BJA and CG | _ | _ | _ |  | ✓made a plan and outline | draft it out a but more | [5 empty] | Final Thesis preparations to submit to Pavia by 20 Aug
| b. Ch 1. Germination Niche (Obj 2) | revise and resend to co authors ✓ | ✓with BJA and CG ✓finish WA notes from B&B ✓parameters from R to SI doc |  |  | ✓Finished Intro and Disc and sent to co-authors | ✓cleaned up R script and annotated for SI | ✓finished draft and sent to BJA. He'll take it from there. | ✓sent script and data files to EFP for his review |  |  | submit to Plant Biology special issue |  |  | Final Thesis preparations to submit to Pavia by 20 Aug
| c. Ch 2. Characterization for seed farming (Obj 3) | prepare and send first draft to co authors. ✓ Stuck on summarizing and displaying phenology data. | ✓with BJA and CG. TZ test to finish PADU quality. ✓ Take final data at Naranjal. ✓ | _ | _ | _ | Read references and organize Draft Disc and Intro |  | DRAFT Finish seed quality data, trying PADU with GA. | DRAFT and send to BJA by 15th |  |  |  |  | Final Thesis preparations to submit to Pavia by 20 Aug | submit to Restoration Ecology.
| d. Ch 3. Species Prioritization (Obj 1) | prepare and send outline and data. ✓ | with BJA and CG. Progress on lookup tables of data. ✓ | ✓Continue populating the data matrix. ✓ Compile Verticillium data and sent to CG for review. | _ |  |  |  | Send latest DEXi scheme to GS. Work on DEXI software with data matrix. |  | Draft | Draft |  |  | Final Thesis preparations to submit to Pavia by 20 Aug | Journal of Arid Environments, AEE?
II. | Soil Seed Bank – Rabanales | _ | take final data collection in greenhouse, data entry ✓ | ✓let soil dry and discard. Clean trays for storage. | _ | _
III. | NASSTEC Handbook | _ | proposed chapters to CG and BJA via email. ✓ | ✓ Discussed and roughly decided handbook titles. Made plan with HA. Ask CH if she would be listed as co-author | _ | ✓wrote drafts and sent to MD and co-authors | awaiting MD review |  | ✓finshed drafts to MD
IV. | Seed Production Manual | _ | _ | ✓Discussed with CG and will later coordinate with AF to populate with data and photos. | [5 empty] | Draft format with AF?
V. | D16 Seeds to seedbank | _ | _ | _ | _ |  | ✓ordered more Si gel granules |  |  | put seeds in SESIL storage with silica after drying in secadero.
VI. | Presentation for SER2017 | _ | _ | ✓Ask INSR board about who could present for me. | _ |  | ✓Send outline to co-authors and a request for their contribution. |  | Put together content from other authors
VII. | Presentation for Seed Quality (NASSTEC Final Conference) | _ | _ | ✓Talk with BJA and CG about a title, session and to submit for plant biology special edition. Done and registered. | _ |  | ✓ Wrote and submitted abstract on seed farming | [9 empty] | Draft the presentation

## NASSTEC host time
|  | 2014-10 | 2014-11 | 2014-12 | 2015-01 | 2015-02 | 2015-03 | 2015-04 | 2015-05 | 2015-06 | 2015-07 | 2015-08 | 2015-09 | 2015-10 | 2015-11 | 2015-12 | 2016-01 | 2016-02 | 2016-03 | 2016-04 | 2016-05 | 2016-06 | 2016-07 | 2016-08 | 2016-09 | 2016-10 | 2016-11 | 2016-12 | 2017-01 | 2017-02 | 2017-03 | 2017-04 | 2017-05 | 2017-06 | 2017-07 | 2017-08 | 2017-09 | TOTAL to date | FINAL TOTAL | 2017-10 | 2017-11 | 2017-12
A | work at SESIL | 12 | 19 | 15 | 17 | 18 | 12 | 10 | 20 | 23 | 19 | 1 | 6 | 16 | 21 | 12 | 19 | 15 | 18 | 24 | 22 | 12 | 1 | 14 | 16 | 11 | 17 | 9 | 20 | 8 | 8 | 17 | 21 | 12 | 21 | 22 | 15 | 473 | 543
A | travel for work | 2 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 4 | 3 | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 33 | 37
B | holidays | 1 | 1 | 3 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 2 | 1 | 3 | 2 | 1 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 37 | 38
B | annual leave | 0 | 0 | 5 | 3 | 2 | 0 | 5 | 0 | 1 | 0 | 0 | 11 | 2 | 0 | 6 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 10 | 0 | 2 | 0 | 1 | 0 | 6 | 0 | 0 | 0 | 60 | 66
B | sick | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
B | weekend days | 4 | 10 | 8 | 9 | 8 | 5 | 7 | 10 | 6 | 6 | 9 | 5 | 6 | 9 | 8 | 10 | 5 | 8 | 5 | 7 | 4 | 6 | 4 | 7 | 10 | 8 | 9 | 9 | 7 | 7 | 10 | 8 | 7 | 10 | 8 | 8 | 234 | 267
C | away work | 7 | 0 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 5 | 20 | 6 | 4 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 10 | 20 | 9 | 5 | 0 | 3 | 0 | 0 | 5 | 14 | 0 | 0 | 3 | 0 | 0 | 5 | 128 | 136
| total days in this month | 26 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 29 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 969 | 1091
| non-work days | 5 | 11 | 16 | 14 | 10 | 5 | 14 | 11 | 7 | 6 | 9 | 16 | 9 | 9 | 19 | 12 | 6 | 13 | 6 | 9 | 4 | 6 | 5 | 7 | 20 | 9 | 22 | 11 | 14 | 7 | 13 | 10 | 13 | 10 | 9 | 8 | 335 | 375
| workable days | 21 | 19 | 15 | 17 | 18 | 26 | 16 | 20 | 23 | 25 | 22 | 14 | 22 | 21 | 12 | 19 | 23 | 18 | 24 | 22 | 26 | 25 | 26 | 23 | 11 | 21 | 9 | 20 | 14 | 24 | 17 | 21 | 17 | 21 | 22 | 22 | 634 | 716
| work host | 14 | 19 | 15 | 17 | 18 | 16 | 12 | 20 | 23 | 20 | 2 | 8 | 18 | 21 | 12 | 19 | 17 | 18 | 24 | 22 | 16 | 5 | 17 | 18 | 11 | 18 | 9 | 20 | 9 | 10 | 17 | 21 | 14 | 21 | 22 | 17 | 506 | 580
| work away | 7 | 0 | 0 | 0 | 0 | 10 | 4 | 0 | 0 | 5 | 20 | 6 | 4 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 10 | 20 | 9 | 5 | 0 | 3 | 0 | 0 | 5 | 14 | 0 | 0 | 3 | 0 | 0 | 5 | 128 | 136
| % away counting travel as host | 33.33% | 0% | 0% | 0% | 0% | 38.46% | 25% | 0% | 0% | 20% | 90.91% | 42.86% | 18.18% | 0% | 0% | 0% | 26.09% | 0% | 0% | 0% | 38.46% | 80% | 34.62% | 21.74% | 0% | 14.29% | 0% | 0% | 35.71% | 58.33% | 0% | 0% | 17.65% | 0% | 0% | 22.73% | 20.19% | 18.99%
| % away counting travel as host | 66.67% | 100% | 100% | 100% | 100% | 61.54% | 75% | 100% | 100% | 80% | 9.091% | 57.14% | 81.82% | 100% | 100% | 100% | 73.91% | 100% | 100% | 100% | 61.54% | 20% | 65.38% | 78.26% | 100% | 85.71% | 100% | 100% | 64.29% | 41.67% | 100% | 100% | 82.35% | 100% | 100% | 77.27% | 79.81% | 81.01%
[38 empty] | 0 | 0
| work host | 12 | 19 | 15 | 17 | 18 | 12 | 10 | 20 | 23 | 19 | 1 | 6 | 16 | 21 | 12 | 19 | 15 | 18 | 24 | 22 | 12 | 1 | 14 | 16 | 11 | 17 | 9 | 20 | 8 | 8 | 17 | 21 | 12 | 21 | 22 | 15 | 473 | 543
| work away | 9 | 0 | 0 | 0 | 0 | 14 | 6 | 0 | 0 | 6 | 21 | 8 | 6 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 14 | 24 | 12 | 7 | 0 | 4 | 0 | 0 | 6 | 16 | 0 | 0 | 5 | 0 | 0 | 7 | 161 | 173
| % away counting travel as away | 42.86% | 0% | 0% | 0% | 0% | 53.85% | 37.5% | 0% | 0% | 24% | 95.45% | 57.14% | 27.27% | 0% | 0% | 0% | 34.78% | 0% | 0% | 0% | 53.85% | 96% | 46.15% | 30.43% | 0% | 19.05% | 0% | 0% | 42.86% | 66.67% | 0% | 0% | 29.41% | 0% | 0% | 31.82% | 25.39% | 24.16%
| % host counting travel as away | 57.14% | 100% | 100% | 100% | 100% | 46.15% | 62.5% | 100% | 100% | 76% | 4.545% | 42.86% | 72.73% | 100% | 100% | 100% | 65.22% | 100% | 100% | 100% | 46.15% | 4% | 53.85% | 69.57% | 100% | 80.95% | 100% | 100% | 57.14% | 33.33% | 100% | 100% | 70.59% | 100% | 100% | 68.18% | 74.61% | 75.84%
| dates of holidays | 13th | 1st | 8th, 24th, 25th | 1st, 6th |  |  | 2nd, 3rd | 1st |  |  | ? Count weekend days that I worked at MSB? |  | 12th |  | 7th, 8th, 24th, 25th, 31st | 1st, 6th | 29th | 24th, 25th |  | 2nd, 27th |  |  | 15th |  | 12th, 24th | 1st | 6th, 8th, 26th | 2nd, 6th | 28th |  | 13th, 14th | 1st, 26th |  |  | 15th